## Tracker
BU Initiative Tracker - FAB-OPS
Proj # | Initiative Name | Initiative Owner | Target Live (FY Qtr) | Budget ($K) | Regulatory (Y/N) | Depends On (codes) | RAG Notes
GIS-0005 | Resilient API Gateway Phase 2 | Avery Romero | FY29 Q2 | 1983 | No |  | On track
GIS-0027 | Edge Data Catalog Refresh | Yara Walsh | FY27 Q3 | 824 | N | GIS-0085, GIS-0074, GIS-0046 | At risk: staffing
GIS-0037 | Secure Endpoint Hardening Refresh | Priya Okafor | FY27 Q4 | 599 | N |  | On track
GIS-0043 | Cloud-First Network Segmentation Refresh | Avery Romero | FY30 Q2 | 840 | Y | GIS-0036 | Dependency slip
GIS-0061 | Identity-Led SIEM Modernization Rollout | Marcus Aziz | FY28 Q2 | 4249 | N |  | At risk: staffing
GIS-0063 | Zero-Trust Backup Resilience Phase 2 | Mateo Moreno | FY28 Q4 | 1300 | N | GIS-0035, GIS-0034 | On track
GIS-0064 | Edge Collaboration Platform Upgrade | Sofia Kim | FY28 Q3 | 881 | N | GIS-0027, GIS-0029 | On track
GIS-0078 | Resilient Patch Orchestration Phase 2 | Yara Chen | FY30 Q2 | 1372 | N | GIS-0082 | Watch: vendor lead time
GIS-0079 | Unified Backup Resilience Program | Marcus Aziz | FY28 Q2 | 1503 | N | GIS-0085, GIS-0082 | Watch: vendor lead time